## Sheet1
Week | Task | difficulty
2020-10-01 | Requirements Engineering | high
2020-10-08 | Create Repository | low
2020-10-15 | Create Flask application | high
2020-10-22 | Create testing and linting | medium
2020-10-29 | Create prediction scripts | medium
2020-11-05 | QA (Check app logs) | medium
2020-11-12 | Create Loadtest | medium
2020-11-19 | Create CD-Pipelines | high
2020-11-26 | Demo (Stakeholders) | medium
2020-12-03 | Documentation | low
2020-12-10 | Bugfixing | high
2020-12-17 | Release | medium
| Goals | Goals
Deliver product on time without bugs
Learn CI+CD principles
Automated testing,build and deployment processes